## Sheet1
April 18, 2019 - May 28, 2019
Link | Key | Feature | Type | Effort
https://github.com/Catrobat/Paintroid/pull/676 | PAINTROID-84 | Fix a crash in the color picker on API < 21 | Bug | 5 | Total Effort | 119
https://github.com/Catrobat/Paintroid/pull/675 | PAINTROID-83 | Fix preview fonts not matching in Font tool | Bug | 5
https://github.com/Catrobat/Paintroid/pull/671 | PAINTROID-80 | Fix cursor is restricted to workspace and not viewspace | Bug | 5
https://github.com/Catrobat/Paintroid/pull/670 | PAINTROID-76 | Fix color picker not working in pipette | Bug | 5
https://github.com/Catrobat/Paintroid/pull/668 | PAINTROID-78 | Fix tool options view broken when soft keyboard open | Bug | 5 |  |  | Team Velocity (Ceiling) | 42.25 | 43
https://github.com/Catrobat/Paintroid/pull/667 | PAINTROID-79 | Fix soft keyboard stays open when switching to fullscreen | Bug | 5
https://github.com/Catrobat/Paintroid/pull/666 | PAINTROID-77 | Fix color picker keyboard does not disappear | Bug | 5
https://github.com/Catrobat/Paintroid/pull/663 | PAINTROID-75 | Fix BaseToolWithRectangleShape ignores rotation when detecting clicks | Bug | 5
https://github.com/Catrobat/Paintroid/pull/657 | PAINTROID-74 | Fix color picker done button text color calculation not accurate | Bug | 5
https://github.com/Catrobat/Paintroid/pull/656 | PAINTROID-72 | Fix line tool preview line does not reset | Bug | 5
https://github.com/Catrobat/Paintroid/pull/655 | PAINTROID-73 | Fix Color picker does not update transparent color in RGB tab when opened | Bug | 5
https://github.com/Catrobat/Paintroid/pull/653 | PAINTROID-58 | Tools with toolbox should click on touchDown position | Bug | 5
https://github.com/Catrobat/Paintroid/pull/652 | PAINTROID-69 | Add missing ContentDescription | Bug | 5
https://github.com/Catrobat/Paintroid/pull/638 | PAINTROID-70 | Prevent crash in Intro Landscape Mode | Bug | 5
https://github.com/Catrobat/Paintroid/pull/637 | PAINTROID-1 | Fix crash when a second MainActivity is started in the same task | Bug | 5
https://github.com/Catrobat/Paintroid/pull/635 | PAINTROID-59 | Fix monospace is not the default font | Bug | 5
https://github.com/Catrobat/Paintroid/pull/634 | PAINTROID-57 | Fix crop tool should also crop on click outside of tool box | Bug | 5
https://github.com/Catrobat/Paintroid/pull/622 | PAINTROID-60 | Fix inconsistent layout padding / margin in tool views | Bug | 5
https://github.com/Catrobat/Paintroid/pull/649 | PAINTROID-68 | Add a resize to canvas tool | Story | 5
https://github.com/Catrobat/Paintroid/pull/664 | PAINTROID-67 | Add a hand tool | Story | 5
https://github.com/Catrobat/Paintroid/pull/650 | PAINTROID-66 | Rename crop in transform tool | Story | 0
https://github.com/Catrobat/Paintroid/pull/642 | PAINTROID-64 | Publish the color picker as a library | Story | 8
https://github.com/Catrobat/Paintroid/pull/647 | PAINTROID-63 | Add HEX color input to the color picker | Story | 3
https://github.com/Catrobat/Paintroid/pull/628 | PAINTROID-41 | No Rotating Icons in for example shape tool | Story | 3
https://github.com/Catrobat/Paintroid/pull/651 | PAINTROID-35 | Add apply and cancel buttons to the color picker | Story | 3
https://github.com/Catrobat/Paintroid/pull/654 | PAINTROID-34 | Add a confirm button to the text tool | Story | 2
March 8, 2019 - April 18, 2019
Link | Key | Feature | Type | Effort
https://github.com/Catrobat/Paintroid/pull/660 |  | Update translations | Bug | 5 | Total Effort | 5
March 4, 2019 - March 8, 2019
Link | Key | Feature | Type | Effort
https://github.com/Catrobat/Paintroid/pull/630 | PAINTROID-61 | Fix a memory leak in fill tool | Bug | 5 | Total Effort | 5
Feb 7, 2019 - March 8, 2019
Link | Key | Feature | Type | Effort
https://github.com/Catrobat/Paintroid/pull/612 | PAINTROID-37 | Add different preview icons for each tool | Story | 2 | Total Effort | 40
https://github.com/Catrobat/Paintroid/pull/611 | PAINTROID-53 | Remove the camera option | Story | 5
https://github.com/Catrobat/Paintroid/pull/610 | PAINTROID-51 | Remove native fill function | Story | 5
https://github.com/Catrobat/Paintroid/pull/607 | PAINTROID-36 | Improve autocrop feedback | Story | 3
https://github.com/Catrobat/Paintroid/pull/605 | PAINTROID-40 | Improve shape tool feedback | Story | 3
https://github.com/Catrobat/Paintroid/pull/592 | PAINTROID-43 | Remove options window for tools without options | Story | 2
https://github.com/Catrobat/Paintroid/pull/614 | PAINTROID-52 | Improve permissions reasoning text | Story | 5
https://github.com/Catrobat/Paintroid/pull/618 | PAINTROID-55 | Disable autoscrolling in fullscreen | Bug | 5
https://github.com/Catrobat/Paintroid/pull/617 | PAINTROID-54 | Long-click on touchDown positon in stamp tool | Bug | 5
https://github.com/Catrobat/Paintroid/pull/621 | PAINTROID-32 | Rename new image to discard image in the integrated version | Bug | 5